## Bug fixes - verified
S.No | Issue title | Status | What the issue was | What we changed | Expected behaviour | How it was verified
1 | Unable to read the text after hovering over "Become a Host" | Fixed - verified | Over the hero image the nav text is forced white, and that rule outranked the hover rule - so hovering added a pale pill underneath white text, i.e. white on near-white. | The hover state now darkens the pill instead of lightening it. | The label stays clearly readable in both normal and hover states, on the hero and on white pages. | Real Chrome, 01-Sep: hovering shows white text on a dark pill.
2 | Zooming in/out on the map triggers a new stay search | Fixed - verified | The map reported every settled view, and the map library raises the same event after a zoom as after a pan - so each zoom re-ran the search and threw away the typed destination. A first attempt guarded this by distance, but its reference point went stale whenever the map moved by itself, which let zooms through AND swallowed genuine pans, so panning stopped searching at all. | The map now listens for the drag-end gesture, which the library raises only for a real drag - never for a zoom, and never for a move the page makes itself. | Zooming only changes the view: the typed location and its results stay put. Dragging the map still re-searches the area you dragged to. | Production: 3 zoom actions = 0 search requests and the heading unchanged; a real drag = 1 search request and the heading changes to "Stays in this map area".
3 | Hotel prices overlap on the map | Fixed - verified | Every stay drew its own price pill with no collision handling, so a busy area became an unreadable wall of overlapping labels. Separately the pills themselves were rendering zero pixels wide, so the text painted onto the map beside the pill instead of inside it. | Pins that would collide are grouped by on-screen distance at the current zoom - a group shows "N stays" and clicking it zooms to that group. Pills are now sized to their own text and centred on their coordinate. | No overlapping labels at any zoom, every label sits inside its pill, and clusters break apart as you zoom in until each stay shows its own price. | Production: zoom 9 = 3 pins, zoom 12 = 4, zoom 15 = 18, zoom 18 = 100 individual prices; no pill zero-width and every label contained.
4 | Search suggestions not displayed for partial location names | Fixed - verified | The place lookup was proxied to OpenStreetMap, which blocks datacenter IP addresses - so every query returned nothing, not just partial ones. | Replaced with a place index built from our own live listings. | Typing two or more characters suggests matching destinations as you type. | Real Chrome: "Delh" returns Delhi, West Delhi, South Delhi and New Delhi.
5 | Guest selection details change after editing the stay search | Fixed - verified | The URL carried only a total guest count (adults + children), so 3 adults + 2 children and 5 adults were the same number - reopening the editor showed 5 adults. | The full party (adults, children, infants, pets) is written to the URL and read back. | The guest breakdown you chose is exactly what you see when you reopen the editor after searching. | Real Chrome: set 3 Adults / 2 Children / 1 Infant, searched, reopened - 3 / 2 / 1.
6 | Irrelevant search results displayed for Uttarakhand | Fixed - verified | Two causes: the broken geocoder left the search with no centre so it widened to about 3,000 km, and the seeded coordinates did not match their addresses. | Fixed the geocoding, gave each place its real centre, and ranked an exact name match above a partial one so a state cannot be outranked by a similarly-spelled neighbour. | Searching Uttarakhand returns Uttarakhand stays, not Uttar Pradesh. | Real Chrome: 100 stays returned, all in ALMORA, Uttarakhand. Note: the seed data spells the state "Uttrakhand" - a content typo worth cleaning up, not a search fault.
7 | Incorrect check-in/check-out dates and pricing on property details | Fixed - verified | The dates chosen during search were not carried through to the property page, so the page priced a different stay from the one searched. | The chosen dates travel with the link and drive both the booking panel and the price quote. | The property page shows the same check-in and check-out you searched, and prices that stay. | Real Chrome: Kullu, 5-10 September 2026 - the property page carried both dates and showed "5 nights".
8 | Share and Save buttons are not functional | Fixed - verified | Both buttons were decoration - neither had any click behaviour attached at all. | Share now opens the device's native share sheet where the browser supports it, and otherwise copies the link and confirms. Save stores the stay, and asks a signed-out visitor to log in first. | Share offers the property link; Save keeps the stay for a signed-in guest and prompts sign-in when signed out. | Real Chrome: Share opened the Windows share sheet; Save while signed out showed "Log in to save this stay".
9 | User can proceed to payment without entering guest details | Fixed - verified | "Proceed to Pay" performed no validation, so empty or nonsense guest name, phone and email went straight through to the payment step. | The three guest fields are validated before checkout and marked as required. | You cannot reach payment until a full name, a valid 10-digit mobile and a valid email are entered, and each failure names what to fix. | Production: empty name, 1-character name, "12345" phone and "not-an-email" were each blocked with their own message and stayed on the review page; valid details proceeded to payment.
10 | Incorrect India map displayed across map pickers | OPEN - needs your decision | The standard OpenStreetMap tiles draw dashed Line-of-Control and Aksai Chin lines around Ladakh and label Gilgit-Baltistan under Pakistani administration. Confirmed by downloading the raw map tiles and inspecting them. | This is painted into the map imagery - no code change of ours can alter it, so it needs a different map provider. The tile setting had been copy-pasted into six places; all six now read one definition, so the switch is a one-line change once a provider is chosen. | Once switched: India shown with its official boundaries on every map on the site. | DECISION NEEDED - Mappls/MapmyIndia (Indian provider, free tier), Mapbox with worldview=IN, or Google Maps with region=IN. Each needs an account/API key.
11 | 404 error while adding a property from Host account | Fixed - verified | Same root cause as #16: step 1 checked the property category against a list hardcoded in the code, while the form itself was built from the admin-managed list. Any category added in the admin panel was therefore rejected the moment you pressed Continue. | Step 1 now validates against the same catalogue the form is built from. | Completing step 1 saves and moves to step 2 for every category the form offers. | Production: step 1 returns success with a new property id for both Homestay and Pool House; an invented category is still correctly refused.
12 | Admin portal does not redirect to dashboard after login | Fixed - verified | The backend issues the role name "super_admin", and the front end's list of accepted roles did not include it - so login genuinely succeeded, then the redirect check rejected the unrecognised role and left you on the login page with a success message. | "super_admin" was added to the accepted roles, and a login submitted on that page now forwards unconditionally. | Valid admin credentials land on the admin dashboard. | Production: login returns success and a token whose role is "super_admin", which the front end now accepts. The final click-through needs a person to type the password - I do not enter credentials into login forms.
13 | Admin login page contains unreadable text | Fixed - verified | A site-wide rule sets every heading to the dark ink colour, and that beat the white colour inherited from the navy panel - so "Admin Console" rendered near-black on navy, a contrast of about 1.03:1. Separately "Admin Login" was drawn with a text-clipping effect over a solid colour, which renders as nothing at all in any browser that does not apply the clip. | The navy panel's headings now inherit its own colour, and the pointless clipping effect was replaced with a plain colour. | All text on the admin login page is clearly legible. | Real Chrome: both headings measure 15.11:1 contrast - comfortably past the AAA accessibility standard.
14 | Improper UI while selecting dates and offer in Send Offer | Fixed - verified | The calendar is 560px wide and its two month grids have a 250px minimum each - 528px that cannot shrink - inside a dialog whose usable width is 428px. It could only spill outside the dialog. | The calendar now fits the container it is placed in, and the two months stack instead of overflowing when there is not room side by side. | The date picker sits fully inside the Send Offer dialog, properly aligned, with no overlap or sideways scrolling. | Production: calendar measures 413px inside the 480px dialog, clear of both edges, with the second month stacked below the first.
15 | Page Not Found after submitting ID verification | Fixed - verified | /verify/complete - the address the identity-check provider returns the host to - was never registered as a page, so it answered 404. The fallback return address also still pointed at a developer's local machine. | Registered the route (marked no-index, as it is a landing page rather than something to be found in search) and pointed the fallback at the live site. | Finishing ID verification lands on the completion page showing the verification status, not a 404. | Production: /verify/complete now returns HTTP 200 (previously 404).
16 | Pool House property category rejected as invalid | Fixed - verified | The add-property form offered 12 categories from the admin panel, but step 1 validated against 11 categories hardcoded in the code - so Pool House, added later in the panel, was always rejected. | Step 1 now validates against the same catalogue that builds the form. | Any category the form offers is accepted, and genuinely invalid values are still refused. | Production: Pool House returns success with a new property id; an invented category still returns "Invalid property category".
17 | Luxe properties displayed when Luxe mode is turned off | Fixed - verified | With LUXE off the request carried no luxury setting at all, so the server returned everything. One of the two listing endpoints also treated the value 0 as "no filter" rather than "exclude luxury". | Normal and LUXE browsing now each send an explicit setting, and both endpoints treat 0 as "exclude luxury". The mobile app was corrected the same way. | LUXE on shows only luxury stays, LUXE off shows only normal stays, and the two never overlap. | Production: the same search returns 7 stays (all luxury) with LUXE on and 23 (none luxury) with it off - 7 + 23 = the full set of 30.
18 | Show on Map does not scroll to the map section | Fixed - verified | The link only selected the Location tab and never scrolled. A first fix scrolled but depended on smooth scrolling and a visibility observer, both of which do nothing in some browsers - leaving the same dead-looking link. | The link now selects the tab AND scrolls, with an instant jump as a fallback if a smooth scroll does not actually move the page. | Clicking "Show on map" selects the Location tab and brings the map into view. | Real Chrome: the page moved from the top to the Location section (scroll 0 to 875), the tab switched to Location, and the map was visible.
19 | [Found during this pass] Picking a destination from the list returned no stays | Fixed - verified | Not on the tester sheet, but more severe than most items that were. The suggestion list hands back a full label such as "West Delhi, Delhi, India", and the results page looked that label up again - but the lookup only recognised bare place names. So choosing ANY suggestion produced "No stays at this location yet", while the same area browsed on the map showed 100 stays. 824 listings sit in the Delhi area alone. | An exact label match now ranks best; an address-style query that finds nothing retries on its leading part; and the coordinates the suggestion already carries now travel with the search instead of being worked out a second time. "Nearby" was also sending coordinates that nothing read - that works now too. | Picking any destination from the suggestion list returns that destination's stays. | Real Chrome: "West Delhi, Delhi, India" returns 100 properties (was 0).