## Read me
Aajoo Homes — tester bug sheet, status as of 15 September 2026 (v3)
This is the sheet Ashish shared ("Aajoo Homes (2).xlsx", 2 September: 19 web rows, 7 app rows) with a status column brought up to date, plus the three items raised on 15 September with screenshots. v2 (2 September) answered the web tab; the app tab had not been answered in a sheet until now.
How to read the Status column:
Fixed · verified on device / live — walked on the live website or on the Android emulator with the build named, with a photograph where one is filed.
Fixed · verified in code + tests — the change is in the build named and pinned by an automated test; the exact screen needs the tester's account (sign-up, OTP) to walk end to end.
Explained — not a defect; what the tester saw is the platform doing what a rule says, and the sheet says which rule.
Where the detail lives: MASTER_PENDING_TASKS.md (sections 8a27–8a32 for this fortnight), AAJOO_CLIENT_REPORTS_RESPONSE_2026-09-15.pdf, and the photographs under report-2026-09-15/.
Current Android build: 95 (aajoo-homes-1.0.0-build95-release.apk). Builds 88–94 are withdrawn.

## Web (19)
S.No | Issue title | Status (15 Sep) | Priority | Severity | Since the 2 Sep verification | Where it was answered
1 | Unable to read the text after hovering over "Become a Host" due to text color | Fixed · verified live (2 Sep, v2 sheet) | Normal | Minor | Still holds. LUXE hover states were re-checked on 15 Sep with the LUXE contrast pass (§8a28). | Aajoo - Tester Bug Sheet - fixes and verification (v2).xlsx, row 1
2 | Zooming in/out on the map triggers a new stay search irrespective of the entered location | Fixed · verified live (2 Sep, v2 sheet) | High | Major | Still holds. | Aajoo - Tester Bug Sheet - fixes and verification (v2).xlsx, row 2
3 | Hotel prices overlap on the map causing a UI issue | Fixed · verified live (2 Sep, v2 sheet) | Low | Minor | Still holds. | Aajoo - Tester Bug Sheet - fixes and verification (v2).xlsx, row 3
4 | Search suggestions are not displayed for partial location names | Fixed · verified live (2 Sep, v2 sheet) | Normal | Minor | Still holds. | Aajoo - Tester Bug Sheet - fixes and verification (v2).xlsx, row 4
5 | Guest selection details change after editing the stay search | Fixed · verified live (2 Sep, v2 sheet) | High | Critical | Still holds; the guest count also survives into checkout and the review page (Sep 5). | Aajoo - Tester Bug Sheet - fixes and verification (v2).xlsx, row 5
6 | Irrelevant search results displayed for Uttarakhand | Fixed · verified live (2 Sep, v2 sheet) | High | Major | Still holds. | Aajoo - Tester Bug Sheet - fixes and verification (v2).xlsx, row 6
7 | Incorrect check-in, check-out dates and pricing displayed on property details | Fixed · verified live (2 Sep, v2 sheet) | High | Critical | Still holds. The whole pricing chain was re-unified on 14–15 Sep (coupon base = the room; cleaning fee stated, not charged) — §8a28, §8a31. | Aajoo - Tester Bug Sheet - fixes and verification (v2).xlsx, row 7
8 | Share and Save buttons are not functional on the property details page | Fixed · verified live (2 Sep, v2 sheet) | Normal | Major | Still holds. | Aajoo - Tester Bug Sheet - fixes and verification (v2).xlsx, row 8
9 | User can proceed to payment without entering guest details | Fixed · verified live (2 Sep, v2 sheet) | High | Major | Still holds; a booking now also carries who is staying (I'm staying / someone else). | Aajoo - Tester Bug Sheet - fixes and verification (v2).xlsx, row 9
10 | Incorrect India map displayed across map pickers | Fixed · verified live (2 Sep, v2 sheet) | Normal | Minor | Still holds; maps moved to Google (region IN) on 2 Sep. | Aajoo - Tester Bug Sheet - fixes and verification (v2).xlsx, row 10
11 | 404 Bad Request error while adding a property from Host account | Fixed · verified live (2 Sep, v2 sheet) | High | Blocker | Still holds; the 5-step wizard is the only listing form on web and app since 8 Sep. | Aajoo - Tester Bug Sheet - fixes and verification (v2).xlsx, row 11
12 | Admin portal does not redirect to dashboard after successful login | Fixed · verified live (2 Sep, v2 sheet) | High | Blocker | Still holds. | Aajoo - Tester Bug Sheet - fixes and verification (v2).xlsx, row 12
13 | Admin login page contains unreadable text | Fixed · verified live (2 Sep, v2 sheet) | Low | Minor | Still holds. | Aajoo - Tester Bug Sheet - fixes and verification (v2).xlsx, row 13
14 | Improper UI displayed while selecting dates and offer when sending an offer to host | Fixed · verified live (2 Sep, v2 sheet) | Normal | Minor | Still holds — and the Send an Offer dialog was rebuilt again on 15 Sep: a week or a month is negotiated as a total, under 7 nights per night (§8a29). | Aajoo - Tester Bug Sheet - fixes and verification (v2).xlsx, row 14
15 | Page Not Found error displayed after submitting ID verification | Fixed · verified live (2 Sep, v2 sheet) | Normal | Minor | Still holds. | Aajoo - Tester Bug Sheet - fixes and verification (v2).xlsx, row 15
16 | Pool House property category is rejected as invalid | Fixed · verified live (2 Sep, v2 sheet) | High | Blocker | Still holds. | Aajoo - Tester Bug Sheet - fixes and verification (v2).xlsx, row 16
17 | Luxe properties displayed when Luxe mode is turned off | Fixed · verified live (2 Sep, v2 sheet) | Normal | Major | Still holds; LUXE now dresses only a LUXE listing and hands the skin back on leaving (§8a28). | Aajoo - Tester Bug Sheet - fixes and verification (v2).xlsx, row 17
18 | Show on Map does not scroll to the map section | Fixed · verified live (2 Sep, v2 sheet) | Low | Minor | Still holds. | Aajoo - Tester Bug Sheet - fixes and verification (v2).xlsx, row 18
19 | Map pickup location fails to load while adding a property | Fixed · verified live (2 Sep, v2 sheet) | High | Blocker | Still holds. | Aajoo - Tester Bug Sheet - fixes and verification (v2).xlsx, row 19

## App (7)
S.No | Issue title | Status (15 Sep) | Priority | Severity | What the issue was, and what changed | How it was verified / what is left to the tester | Reference
1 | Email input UI overlaps at the top during sign-up | Fixed · verified on device (build 13, 4 Sep) | Normal | Minor | The keypad's height was reserved three times over — the card subtracted it, the scroll view padded by it again — leaving the field hard against the top. The card now reserves only the part the route has not already excluded. | Build 13 (4 Sep). Verified on the emulator on build 13 with the keypad up: the card runs to the top of the keys with no gap. Not re-walked on build 95 (needs a signed-out device; the emulator holds the tester's signed-in session). | app commit 6b47fef (APP #15)
2 | Host signup fails on the first attempt with an incorrect age restriction error | Fixed · verified in code + tests (2 Sep; and again 15 Sep) | High | Blocker | Two causes, both closed. (a) The date-of-birth wheel opened on TODAY and only wrote a date when scrolled — tapping Done unscrolled submitted age 0, and the second attempt worked because the wheel had moved by then. It now opens on the youngest date that is old enough and cannot go younger. (b) On 15 Sep a second failure was found: the app sends DD/MM/YYYY and the server read it with JavaScript's Date, which takes '25/06/2001' as month 25 — every birthday after the 12th of a month was refused. The server now reads the three spellings the clients use. | Build 95 carries both. (a) app commit 0b6a5ac; (b) backend 10d755c, pinned by aBirthdayIsReadTheWayItWasWritten.test.js (7 checks). Sign-up itself needs a new account to walk, which is the tester's to do. | app 0b6a5ac (APP #2); BE 10d755c; master list §8a30
3 | Don't have an account? Sign Up is hidden behind navigation buttons | Fixed · verified in code (2 Sep) | Low | Minor | The login card is pinned to the bottom of the screen and its own padding was a fixed 24, so the last row sat under the system navigation bar. The padding now adds the navigation bar's own height (viewPadding.bottom). | Build 13+. Code comment records the tester's report. The login screen needs a signed-out device to photograph; the same fix on the profile screen (row 4) IS photographed on build 94. | app eb8eb39 / fd85dc6
4 | Update Profile button is hidden behind navigation buttons | Fixed · verified on device (build 94, 15 Sep) | Low | Minor | Same cause as row 3 on the Edit Profile screen: the scroll area's bottom padding was fixed, and the navigation bar drew over the button. It now adds the bar's height. | Photograph report-2026-09-15/app/build94-edit-profile-button-above-nav.png — Update Profile fully visible above the bar, on the tester's account. | app eb8eb39 / fd85dc6
5 | Confirm button UI is broken on OTP verification tab after clicking Update Profile | Fixed · verified in code (4 Sep) | Low | Minor | The OTP sheet double-counted the keypad (the same pattern as row 1), which pushed the Confirm button out of its box. Fixed with the same measurement — reserve only the shortfall the route has not already excluded. | Build 13+ (APP #5, the correction row 1's commit refers to). Walking it end to end sends an OTP to the account's email; left to the tester. | app 6b47fef (notes APP #5)
6 | Profile changes are not saved after phone number update and OTP submission | Fixed · verified in code (reproduced on a real account) | High | Blocker | The save was never attempted: the form's validation failed on Last Name / State (which were empty on the account), the errors rendered a screen and a half above the button, and the button appeared to do nothing. The screen now says 'Please fill the highlighted fields above' and scrolls to the first one; a valid form saves as before. | Reproduced on an account with empty Last Name and State, then fixed (update_profile_screen.dart). The phone-change branch needs the emailed OTP to walk end to end; left to the tester. | update_profile_screen.dart; master list §8a27
7 | Enabling or disabling one house rule toggle changes all house rule toggles | Fixed · verified in code + tests (2 Sep) | High | Critical | The listing schema names the identifier 'value' on most lists but 'key' on the house-rule toggles, and the app read only 'value' — so all ten toggles parsed with an EMPTY id and shared one entry. Flipping any flipped all, and every listing filed from the app stored its house rules under ''. The parser now accepts 'key'; each toggle writes its own rule. | Build 13+. The wizard was then rebuilt (8–10 Sep) with one toggle per rule (toggleHouseRule(key, v)); the 14 affected house-rule rows were checked (all test listings). The host wizard needs a host sign-in on a device to photograph; not on the tester's renter session. | app 0b6a5ac (APP #7); master list §8a25–27

## 15 Sep items (3)
# | Report | Status | What was seen, what was wrong, what changed | Verification / reference | Platform
1 | Home page cards: 'equal sizes of cards and a little smaller, 6–7 show, across platform' | Fixed · deployed 15 Sep (web); app already equal | Web: the Trending / Nearby / Featured rails showed four cards of four heights — one address wrapped to two lines, one card had no cancellation badge. Rail cards are now 196px with a 14px gap (six in the 1320px container, the seventh peeking), the address and the title clamp to one line with the whole text as a hover tooltip, the cancellation badge keeps its slot on every card, and the row stretches its cards to one height. On a phone the web rail shows two cards, like the app. App: the home rail was already 200dp cards of one fixed height with one-line text. | Web commit 2880a35, pinned by railCardsAreEqual.test.mjs; live photograph in the master list §8a33. | Web
2 | 'No booking currently on, but it shows accepted and offers a deal' | Explained + fixed a dead end (web, 15 Sep) | The deal was real: DEAL29302101C175, 7.9% on QA Sunrise Villa for 15→22 Sep, struck at 06:38 on 15 Sep on the test guest account 'Aajoo Renter' (aajoo.renter1@…, user 101) — by our own live test of the weekly-negotiation change that morning, on the same test account you were signed in with. It expired at midnight. What WAS wrong: with no dates picked, the card said 'pick the agreed nights to use it' and at the same time locked the date boxes ('your deal is agreed for these dates, so they cannot be changed'), so the nights it asked for could not be picked. Now: a dated deal fills the empty date boxes with its own dates, the boxes are locked only while the deal actually applies to the dates on screen, and the mismatch banner offers 'Use the agreed nights' with one click. | Web commit 2880a35, pinned in aDealPricesOnlyItsOwnNights.test.mjs. Going forward our live tests will use the 'Renter test web' account (179), not the client's test guest (101). | Web
3 | 'Check-in 16, the 17th is blocked, check-out 18 — but the host side shows no booking or block on the 17th' | Explained (web) · Fixed for parity (app, build 95) | There is no booking and no block on QA Sunrise Villa (checked in the database and on /booking/property-availability: bookedRanges is empty). The 17th greyed out as a CHECK-OUT because the listing's own rule — set in step 5 of the wizard — is a minimum stay of 2 nights: after a 16th check-in, 16→17 is one night, so the earliest check-out is the 18th. The website's calendar says this under the grid ('Minimum stay 2 nights') and in the header once a check-in is picked ('Minimum 2 nights — check out 18 Sept or after'). The host's calendar shows no block because it is not one. Parity gap found on the way: the Android app read neither the minimum nor the maximum stay, so it let a guest pick 16→17 and be refused at booking. Build 95 applies both in the check-out picker and says the rule under the date rows, in the website's words. | App commit (build 95), pinned by the_minimum_stay_is_a_rule_not_a_block_test.dart; driven on the emulator on 29302 (16 → 17 refused, 18 offered). | Web · App