## User
|  |  | Status | What changed (dev · 16 Aug 2026)
Dditt KYC |  |  | DONE (earlier) | DIDIT KYC live on both platforms; re-verification fixed — Profile → Update documents runs DIDIT (server 'force' flag added).
Loader On app Opening ( Castle Image is appearing ) |  |  | PARTIAL — needs your asset | Castle image gone: splash now shows the official logo. The branded loader animation itself is still awaited from Aajoo (Lottie preferred).
Change Price button chip on map in Homepage |  |  | DONE (earlier) | Map price markers redrawn as gradient ₹ speech-bubbles with shadow + shine.
Change Map Desgin acc to current app trend |  |  | OPEN — design scope | Full map restyle is redesign work, not a defect; needs a design direction.
Fix City and State Id Management in DB |  |  | DECISION NEEDED | States corrected 12 Aug; ~4,260 junk city labels remain. Proper fix needs the Google Geocoding key (enabled, awaiting billing) + your catalogue decision (keep/trim/remove the 29k import).
Break Down Sign up Process |  |  | OPEN — design scope | Signup restructure is a UX design task; awaiting the flow you want.
Swap cat. and find your stay section, fix category on top on home page |  | ss | DONE (earlier) | Home reordered — single category row sits directly under search; duplicate second row removed.
Re design the property cart on homepage (optmize)also add neccesary info in cart/ tags cat |  |  | DONE (earlier) | Property card rebuilt: verified badge, real rating or 'New', category tag, price — and now a gold 'Sponsored' chip for boosted listings.
Change catergory icon, Name also in admin | Cat. Listing |  | DONE (earlier) | One consolidated icon map (two disagreed before); categories are API-driven and admin-manageable; legacy occupancy types hidden from browse.
Change Filter according to current trend remove weekly and montly filter (re-design) |  |  | PARTIAL — conflicts with Common #14 | 'Weekly' removed everywhere (Per night / Monthly only). Common sheet row 14 asks to ADD monthly/per-night chips — the two asks contradict; tell us which wins.
Fix re-center button on map |  |  | DONE (16 Aug) | New re-center button on the map (top-right); takes a fresh GPS fix and re-syncs the property search. Verified on emulator.
Check notificaation all across Platform |  |  | DONE (earlier) | Notification icon in header, in-app notification centre for guest/host/admin, push wired via Firebase.
whishlist |  |  | VERIFIED — already works | Wishlist is fully wired: heart toggles /properties/user-saveProp, Saved page lists /user/saved-properties (tbl_saved_liked_prop).
Re desgin nav bar, add Hii messeage with user Name |  |  | DONE (earlier) | Branded header + 'Welcome back, {first name}! 👋' greeting on the dashboard.
Use relatable SVG , illustrations |  |  | PARTIAL | Host 'no ongoing bookings' now has an animated illustration (16 Aug). A full illustration pass across empty states = design scope.
Side Bar |  |  | DONE (earlier) | Side drawer removed; its pages moved to the Profile menu (they were only reachable by tapping the logo before).
Fix social Media Section In bottom according to every device ( SS in Device) |  |  | DONE (16 Aug) | Social icons now actually open (Android 11 package-visibility fix) and point at the real handles, same as web.
Change icon |  |  | NEEDS CLARIFICATION | Row says only 'Change icon' — tell us which icon and to what.
In top section show users profile details, Like Number Host/user edit icon |  |  | DONE (earlier) | Profile top section shows avatar, name, phone, host/user role and edit.
Dicussion on sidebar listing |  |  | DISCUSSION | Sidebar was removed into Profile — raise anything still to discuss.
help & support contact Dicussion |  |  | DISCUSSION | Support screen rebuilt (call, WhatsApp, chat, email); discussion open on contact numbers/addresses.
Social Media Icon issue in help and support page |  |  | DONE (16 Aug) | Root cause: manifest lacked Android 11 <queries>, so canLaunchUrl said no and taps died silently. Fixed; icons verified opening externally.
About US |  |  | — | Section heading
Re desgin about US page |  |  | DONE (earlier) | About Us is CMS-driven and identical on app + website; old divergent copy deck retired.
Settings |  |  | — | Section heading
Remove about us |  |  | OPEN — quick change on your word | About Us still listed in Settings. It also lives on the Profile menu now — say the word and the Settings entry goes.
Add Changes According |  |  | NEEDS CLARIFICATION | 'Add Changes According' — no referent; tell us what to change.
Fix rate app Button |  |  | DONE (16 Aug) | Rate App tile had an empty tap handler. Now opens the Play Store listing (market:// with https fallback) or says why it can't.
Common Issues |  |  | — | Section heading
improve document uploading system |  |  | DONE (earlier) | Manual document upload sheet (381 lines) replaced by DIDIT-driven verification with proper status chips.
Specifiy image should be in landscape or make in land scape |  |  | OPEN — needs a rule | Decide: enforce landscape at upload, auto-crop, or leave free — then we implement the validation.
Properties Details |  |  | — | Section heading
Set the font and icon, Button size (its too Big) |  |  | DONE (earlier) | Property page rebuilt on the new theme — type scale, icons and buttons resized.
When Scroll Up catergortyy and rating section disappear |  |  | BELIEVED FIXED | The tabbed property-page rebuild replaced the collapsing header. Reopen with steps if it still occurs.
replace the save button with whish list icon |  |  | DONE (earlier) | Save button is a heart wishlist icon, synced to the backend (not local state).
Make gallary on little top when click on the image image should be open |  |  | DONE (earlier) | Swipeable gallery with counter/dots near the top; images open. No photos = no gallery (never a stock image).
add attarction points |  |  | DONE (earlier) | Nearby attractions from property_nearby_places; admin can enter them (Admin → Properties → Nearby).
Add cancallation policy button |  |  | DONE (earlier) | Policies tab on the property page; full cancellation-policy system (tiers, refund ladder) shipped.
Fix the bottom price section , Its overlapping with mobile back button screen |  |  | VERIFIED — already safe | Bottom price bar already offsets by the system gesture inset (MediaQuery bottom padding).
Booking Detail Page |  |  | — | Section heading
dicussion on booking change |  |  | DISCUSSION | Booking-change/reschedule flow — needs a product discussion before build.
Sockets |  |  | — | Section heading
Change loader display when click on offer your price |  |  | DONE (earlier) | Negotiation loader could spin forever (cleared only by a socket event that never came on first offer). Fixed + 12s watchdog.
Razor Pay |  |  | — | Section heading
As per current market |  |  | DONE (16 Aug) | Checkout is standard Razorpay modal — and now supports wallet split-payment (wallet covers what it can, gateway charges the rest).
On going |  |  | — | Section heading
On going page |  |  | DONE (earlier) | Ongoing page has the stay map inline + working action buttons.
Only one, current ongoing booking should be applicable for pay on arrival, when on pay on arrival booking is active otrher bookings should not be applicable for pay on arrival |  |  | VERIFIED — enforced server-side | Only one active pay-on-arrival booking per guest (backend guard) + app-side status logic fixed to match.
if user want to choose multiple POA ask user to swtich on Subscprtion model | Pending |  | DECISION NEEDED | 'Multiple POA via subscription' = a subscription product that doesn't exist yet. Needs a business decision + pricing before build.
fix on goining pop on homepage add view all button |  |  | DONE (earlier) | Ongoing widget on home with View all.
Cancel Booking Page |  |  | — | Section heading
As per current market |  |  | DONE (earlier) | Cancellation flow rebuilt: policy-based refund %, wallet-first refunds (16 Aug), money notices to both sides.
Show location on map nearest booking |  |  | DONE (earlier) | Confirmed/ongoing screens lead with the stay map + Get Directions.
Avoid Multipple booking / |  |  | VERIFIED — enforced server-side | Date-overlap guard blocks double-booking, incl. a 30-min hold on payment-pending checkouts.
Add Block calender for current booking for all other OTA as well |  |  | PARTIAL | Internal calendar blocking done (booked ranges greyed in the picker, availability endpoint live). Cross-OTA iCal sync with other platforms is NOT built — separate feature, needs a decision.
Pre Booking - |  |  | — | Section heading
Improve listing Icons text, Font |  |  | DONE (earlier) | Pre-booking screen rebuilt on the new theme.
Use the same icon as on Home page |  |  | DONE (earlier) | Shared icon set with home.
Use same card design as on home page |  |  | DONE (earlier) | Same shared property card as home.
make filter section small |  |  | DONE (earlier) | Filter section compacted in the rebuild.
Show loader when scroll listing |  |  | DONE (earlier) | Shimmer loaders on scroll/load.
Add state listing according to user current loaction (make small chips of states also user and filter property according to selection |  |  | DONE (earlier) | Area rails (Shimla, Kufri, Mohali, Panchkula, Kharar, Chandigarh) + destination search; 12 properties per rail, verified on production.
Improve filter button |  |  | DONE (earlier) | Filter button redesigned.
LUX |  |  | — | Section heading
Make Chnages in Desgin when user is in LUX Mode Change UI Accordingly |  |  | DONE (earlier) | Full LUX theme: near-black + gold, its own loader, icon swap, slower motion.
Sign Up User / Host |  |  | DONE (earlier) | Sign-up carries a Renter/Host toggle; host KYC at signup, renter KYC at booking.
Forget Password |  |  | DONE (earlier) | Forgot-password overhauled: 6-digit parity, OTP expiry + guess limits, no membership oracle. SMS path built — awaiting your SMS provider creds.
Menu Icons According to current market |  |  | DONE (earlier) | Menu iconography modernised in the redesign.
History Page Map current Market |  |  | NEEDS CLARIFICATION | History page was redesigned; tell us what 'map current market' should look like specifically.
Safety Page Design |  |  | DONE (earlier) | Safety page built on BOTH platforms, CMS-editable — false safety claims (emergency button, insurance, verification promises) removed.
About Page Design |  |  | DONE (earlier) | About page matches the website via shared CMS.
Same for Host |  |  | DONE (earlier) | Host portal fully redesigned: shell, dashboard, bookings, negotiations, messages, payouts, profile.
Sockets |  |  | DONE (earlier) | Negotiation socket flow hardened; admin can now read negotiation messages (endpoint added).
Duplicate Pages |  |  | PARTIAL | Dead-code purge removed 41 unreachable app files (verified by import graph). Remaining duplicate filenames are mostly safe re-export shims; case-by-case cleanup continues.

## Aug 08-26
Admin Dashboard | Status | Status | What changed (dev · verified against live system)
Payouts |  | — | Section heading
Host name is not appearing in payout detail page | Pending | DONE | searchPayouts returned raw rows with no host join — UI fell back to 'Host #100'. Join added; real names verified.
add a option to see detail of payout like host detail, booking detail, user detail , host bank detail of host etc, | Pending | DONE | Full payout detail screen built: host, booking, user, masked bank details. (Bank table had zero rows — the host form posted to an endpoint that discarded them; that's fixed too.)
period show invalid data | Pending | DONE | Period fields were NULL on 6 of 8 payouts and never set by initiatePayout. Now written.
Payout is not working (if i try to pay to the host its not working please fix the then need to be restest as its payment related critical thing it should not hold any error and operation should be smooth | Pending | DONE | Route mismatch: client called PUT .../approve/{id}, server served .../{id}/approve — every attempt 404'd. Same for reject. Fixed; payouts now need only the RazorpayX credentials to move real money.
In Invoice section, Download invoice is not working (due to this we are nto able to see the format and other info of invoice | Pending | DONE | Two faults: the button only rendered if a never-populated pdf_url existed, and the download endpoint path was inverted. PDF generation itself was fine. Both fixed; invoice downloads verified.
all exported report related to finance, should show the period on top of export file to show for which period this report belong to (eg. i generated cashflow report and its name say 08-08-2026 but i applied the filter for different report) | Pending | DONE | Every finance export now opens with report name, period covered and generation time.
User |  | — | Section heading
Actice/Inactive on off button is not working properly | Pending | DONE | null-vs-undefined bug: switching a filter OFF re-sent the stale filter. Fixed.
Document number validation is not working as expected it should be based on document type | Pending | DONE | Client had a bare required() while the server validated per type (Aadhaar 12 digits, DL, passport). Client now mirrors the server.
error message should be belong to error like i did not upload the image so its show failed to add user, if its say image is required its look more user friendly | Pending | DONE | 422 replies carry an array of field messages; the UI read it as a string and always showed the generic error. Real messages now surface (shared apiErrorMessage).
i send a negtiation message to host, where can i check the message | Pending | DONE | Nowhere — negotiation messages were written by the socket and readable by nothing. New Admin → Negotiations → Messages screen; threads open inline.
HOST |  | — | Section heading
Chage the name of for to add New Host | Pending | DONE | Modal ignored its context prop — adding a host was headed 'Add New User'. Fixed.
Add host form is not working see SS (Screenshot 2026-08-08 230857.png) | Pending | DONE | Server requires a password; the client rule was commented out, so the form posted blank and 422'd (with the error hidden by row 12's bug). Fixed.
Update, Host-update form title | Pending | DONE | Same title fix; host branch also gained its missing success message.
PROPERTY |  | — | Section heading
Description points are not comming after saving the form, if you leave the page and come back the Description Points disapear | Pending | DONE | Not persistence — the submit handler never sent the 'extra' field, so every save wrote undefined. Now sent.
Same problem with property document image upload | Pending | DONE | Documents were written to one table and read from another. Unified; existing docs now appear.
Pet friendly and Smoking free dropdown remain unchanged after save | Pending | DONE | Same cause as row 19 — the two fields were never sent, so both reset to 0 on every save.
After deleting Host, property still show the host name, please also delete the host from that property and mark status as inactive | Pending | DONE (partial by design) | Listing marked inactive + host name carries a 'deleted' badge. The host id is deliberately kept — booking/finance history reaches the host through it; say the word if you want it nulled anyway.
Logo is not show up on email | Pending | DONE | Templates pointed at a placeholder domain that never resolved. Now the real (new) logo, served un-hashed so it survives deploys.
Host Dashboard (different from Admin Dashboard) |  | — | Section heading
Settings |  | — | Section heading
Host full information is not pop up on profile like phone number, city, address | Pending | DONE | The server always returned and accepted address/phone/city — the form simply had no fields. Added.
Login |  | — | Section heading
i am not able to LOGIN as user when user is not verified | Pending | DONE | Unverified login said 'No record found'. Now re-sends a fresh code and routes to verification — password checked first so it can't probe which emails exist. Fixed on app too.

## Aug 08-26 App
Findings | Status | Status | What changed (dev)
When open app |  | — | Section heading
change the loader |  | BLOCKED — your asset | Swapping the loader is one line; we need the branded animation file (Lottie).
add ringtone/bell tone provided by us / sharing on whatsapp |  | PARTIAL — your asset | WhatsApp sharing DONE (system share sheet). Custom ringtone needs your audio file — and a new notification channel id, since Android caches channels.
Change the logo from the app icon / inside and outside the app |  | DONE (15 Aug) | Official logo everywhere: launcher icon (adaptive), splash, in-app, web favicons, emails.
Landing Page add slide instead of single image |  | DONE (earlier) | Landing page runs a 3-image auto-playing carousel.
Sign up |  | — | Section heading
Phone number verification missing |  | BLOCKED — client | Needs an SMS provider + India DLT sender/template approval. The backend SMS service is built and waiting for credentials.
Fix the google sign in the login page |  | NO DEFECT FOUND | Package name, both SHA-1s, serverClientId and backend all verified correct. If it fails on a Play Store build, that build's App-Signing SHA-1 must be added in Firebase.
signup with google is missing when new account create |  | DONE | The Google button existed but wasn't rendered on the sign-up tab. Now on both, 'Sign up with Google'.
When i signup my account without OTP my account is generated / but gave me error |  | DONE | Real cause: Google sign-in created the account and sent the welcome email BEFORE its gates ran, so a refusal left a half-created account + an error. Gates now run first.
Signup is not done i recieved the email that my account is created and complete the profile |  | DONE | Same root cause as the row above; fixed together.
Forget |  | — | Section heading
When i Forgot the password in the screen it shows 4 digit to fill and when i recieved the email there shows the 6 digit |  | DONE | Server moved to 6-digit OTPs; the app still demanded exactly 4 in four places. All aligned.
Phone No forgot Password is missing |  | BUILT — awaiting SMS creds | Phone-number reset built end to end (shared OTP/lockout with email). Sends the moment SMS credentials exist; until then it says so and points to email.
Fix all the Forgot System |  | DONE | Audit: reset OTP had no expiry and unlimited guesses (weaker than signup!). Expiry + attempt caps enforced; email failures no longer report success; no membership oracle.
Renter |  | — | Section heading
Show Properties in maps as per current location |  | DONE | Map fallback was Mountain View, California (emulator default) — could sit 12,000 km from the fetched properties. Declining location also fetched nothing at all. Both fixed.
Show Current Loaction instead of Goa |  | DONE | 'Goa' was hardcoded. Real place via geocoder; 'Nearby' until it resolves.
Add notifiaction icon on the top right instead of profile icon |  | DONE | Was a profile icon that opened notifications. Now a bell.
This week tab |  | — | Section heading
Show current real data in the tab |  | DONE | '1,240 verified homes' was hardcoded. Real nearby count + place now.
18 new property also in real time |  | DONE | '18 new this week' was invented; nothing measures it. Removed rather than faked.
remove the reloctor button and fix into the app |  | DONE | Standalone relocator button removed (pull-to-refresh + map controls do the job).
Browser by cat. |  | — | Section heading
Show all the icon that show below and only 1 time remove from below and add these into one where 1st fix |  | DONE | The two category rows weren't duplicates — the top one was hardcoded and filtered nothing. One API-driven row now, and it filters.
Fix all the cat. icons a |  | DONE | Two disagreeing icon maps consolidated into one.
Fix the Pre Booking & Lux Buttoon Below the Browse by Cat. |  | DONE | Pre-Booking + LUX toggle sit directly under the category row.
Properties in your current locations |  | — | Section heading
show Properties in the slider and gave the see all button top right / Show 10-12 properties |  | DONE | Slider rails with 'See all' top-right, 10–12 properties.
Then show Curated For you |  | DONE | 'Curated for you' rail added.
show Properties in the slider and gave the see all button top right / Show 10-12 properties |  | DONE | Same shared slider component.
Show Blogs 4-5 and top right add see all and go to blog page |  | DONE | Blog built on app AND web (/blog); home strip shows 4–5 with See all.
Show the FAQ and end the page. |  | DONE | FAQ strip closes the page.
Property Detail page |  | — | Section heading
Property namse show the verified badage |  | DONE | Verified badge beside the name — driven by real verification status.
in the app show all the properties deteilas like website |  | DONE | Full details incl. map and policies (app never had them).
About /aminities / hose rule / location/ reviews/ host/ ploices in diffrent tables like webiste |  | DONE | Tabbed sections like the website.
do not show all of the above in long page add these of above in listing like: |  | DONE | Real tab panels (web's were jump links; now real on both).
if user clkick on the about shoe property dicption only, if user click on amanties shows aminties only and show on |  | DONE | Each tab shows only its own content.
Instead of reviews mention customer/user experinces |  | DONE | 'Guest experiences'.
Then show gallary into |  | DONE | Swipeable gallery.
show near by attaraction places |  | DONE | Nearby attractions from the listing data; admin-editable.
Show distance from / near airport/ near hospital/ near park/ bus stand |  | DONE | Distances to airport/hospital/park/bus stand; sub-km in metres.
show property blog pages |  | DONE | Blog strip on the property page.
Reserve Page |  | — | Section heading
View Details: Booking shows Daily weekly monthly/// Mention instead of daily, pernight and monthly remove weekly |  | DONE | 'Per night' / 'Monthly'; Weekly removed.
Check in- out time is fixed by host remove the edit icon only/ its fixed already |  | DONE | Edit icon gone; reads 'set by the host'.
Below the Total Price don't show any price nothing |  | DONE | Removed — it was showing the host's private negotiating band under the guest's price.
if user select the monthly do not chnage the price below, price change according to the dates and set by host |  | DONE | Monthly no longer multiplies price ×30 (a 1-night stay 'cost' ₹96,000). Dates × host rate decide.
Price various on the Minmun price, Ideal price, Maximun Price/ monthly Price / weekly price only for host not for user show accordngy of user booking stay for 7 days |  | DONE | Min/Ideal/Max prices are host-side only now.
instead of reserve show the negotiate & Reserve |  | DONE | 'Negotiate & Reserve'.
Then shows the Book now and negotiate button Fix the negoatition buttion do n't show loader of negoation |  | DONE | Loader could spin forever waiting for a socket event that never came on a first offer. Fixed + watchdog. (Also found here: hand-picked dates billed one night too many — fixed; no real guest was affected.)
KYC |  | — | Section heading
When I click on book now or Negotiate Asking for KYC I Have done with the KYC from the app i didn't get my previous page where i left my booking before booked a property |  | DONE | Booking intent saved to disk before DIDIT hands off to the browser; a 'Finish your booking' banner restores it — Android may kill the app during KYC.
When I'm a new user why it shows one time POA Beacuse I'm only booked i property, if user book more than 1 property then at that time show the POA policy |  | DONE | The app counted abandoned checkouts as active bookings (status-title string matching). Keyed on status ids now; POA message only when genuinely applicable.
When i'm done with the booking , booking confrim page in missing in real time booking and send email once the booking is done for both the ends user and host |  | DONE | Online-paid bookings completed silently — confirmation emails only fired for pay-on-arrival. Both sides now get email at payment verification; hosts had never received one.
Booking confrimed page is missing show the get direction icon and the maps inside the app as per the refrence image |  | DONE | Confirmed page is a real route (was a dialog that could miss) with map + Get Directions. Directions no longer launch at 0,0.
When i done with the booking ongooing page missing on the maps |  | DONE | Ongoing page has the map inline.
LUX Mode |  | — | Section heading
Lux Mode Make some diffrence in colors and icons and animations some diffrenteant from the standrad / fix a loader like it show lux |  | DONE | LUX theme: near-black + gold, own icons, slower motion, gold LUX loader.
LUX Page same as the standard PAge only/ make it feel like LUX experince |  | DONE | Switch dialog dressed for the direction; LUX loader holds until luxury listings land.
Prebooking : Page |  | — | Section heading
Current location is editable and show same like fic the home page and Browse by category. |  | DONE | Location editable via the same pill + destination search as home.
Chnage the Browser by catgeory into homestay villas remove single couple etc |  | DONE | Real property types; single/couple/party hidden from browse (not deleted — 10 live listings carry them).
Fix the LUX button Top Right with the search that chnage of mode from there |  | DONE | Animated LUX toggle top-right by search.
In the prebooking show the properties in slider by areas |  | DONE | Area rails, each loading independently.
Shimla/ Kufri / Mohali, panchkula/ mohali/ Kharar |  | DONE | Shimla, Kufri, Mohali, Panchkula, Kharar, Chandigarh. Kufri has zero listings on the platform, so its rail hides until it does.
show all the areas types in the slider and show 10-12 properties in slide |  | DONE | 12 per rail; matched on address area (city match returned 0–1 rows). Verified on production.
in the prebooking gave the check in check out dates select to the user |  | DONE | Check-in/out picker added; dates carry into the property page.
My booking Page |  | — | Section heading
Chnage the all the tabs as per the current theme |  | DONE | Tabs restyled to the current theme.
Upcoming stay / Ongoing page / Completed / Cancelled |  | VERIFIED — already correct | Four tabs existed and bucket on stay dates (not status titles), which is what keeps finished stays out of Upcoming.
User click on the view on the details page |  | VERIFIED — already works | View Details opens the booking with its property.
Show the support button and host chat button and host details below the booking if TAB but not in the cancelled Show there book now button only do not show the Host details |  | DONE | Support + Chat-with-host + host card under the booking. Cancelled: book-now only, no host details. (Support kept on Cancelled — refunds are support questions; say the word to remove.)
Show the all property page below all of the above mentioned |  | DONE | Same seven property panels as the property page — one shared implementation, so they can't drift.
Show property photos instead of maps |  | DONE | Swipeable photo gallery leads; the map stays under Location.
Menu |  | — | Section heading
Remove right side menu and fix this menu below the profile page where all pages exits |  | DONE | Drawer deleted; all its pages live on Profile. (It had no menu button — it opened by tapping the logo.)
Safety, about us pages same as the website |  | DONE | Safety + About shared with the website via CMS. Old safety copy claimed an emergency button, insurance and verification programmes that don't exist — removed on both platforms.
Prolie Page |  | — | Section heading
When USer want to Update the documents do KYC again FIX Diddit |  | DONE | Server had a 90-day 'skip' with no opt-out, so re-verification returned no session and the app blamed an outage. 'force' flag added; Update-documents now runs DIDIT; 'Verified' chip reads the real decision.
give location to auto fill the current location / or by Zip easy for user reduce time to fill the info. |  | DONE | 'Use my location' + 'Fill from PIN' buttons autofill address/city/PIN via the platform geocoder (no new API cost).
Host |  | — | Section heading
My booking page |  | — | Section heading
Upcoming/ ongoing/Completed/ Cancelled in these of when User click on the view details tabs (Same as user where gave the property details and Support button and all ) |  | DONE | Host bookings got a real detail page with the same property panels as the guest side.
In this gave the user details and Support and User chat button below that show the property details ( ongoing page like user side) |  | DONE | Needed a backend fix first: /host/booking-history returned neither property id nor user id. Now guest details, Support, Chat-with-guest, property below; Cancelled hides the guest block.
Dashboard |  | — | Section heading
Instaed of Transacation show negaoation tab where user can find all the negioataion |  | DONE | Negotiations tab on the dashboard + full screen. The endpoint existed and nothing called it — a missed push meant a missed offer. 13 live offers surfaced.
Show 4-5 trancation only below show the FAQ |  | DONE | Transactions capped at 5 with View-all; FAQ closes the page.
total booking is not working show the graph weekly and monthly bookings to the host |  | DONE | Weekly/monthly bookings trend card built from data already loaded.
ongoing stays/property /buttons are not working |  | DONE | All four stat tiles were dead containers; each now opens its screen.
Check more nesscary points that we can show in the host dashboard |  | PARTIAL — pick from the shortlist | 4th tile became 'Offers to review' (the only number with a decision attached). Five further candidates proposed (upcoming check-ins, nights vs last month, achieved vs asking rate, invisible listings, unanswered reviews) — awaiting your pick.
Support //// Messeages insetad of the support |  | DONE | Support tab rebuilt as Messages.
In the messeage show the aajoo support button on top and other user cionverstaion below |  | DONE | Aajoo Support pinned on top; guest conversations (negotiation threads) below.
List your property page as per the Website fixed in the app, Then we have gave the final look for the Property form as per SEO we have to add the Property Form |  | NOT STARTED — blocked on your design | Porting the app onto the website's 5-step Listing Engine (~15 endpoints, 24 tables) is feature-sized work, and the 'final SEO look' design referenced here was never shared. Needs the design + a go decision.
Menu |  | — | Section heading
All the menu pages show in the Host Profile page |  | DONE (earlier) | Host menu pages live on the host Profile.
In the host profile gave the menu on the top of the right side |  | DONE (earlier) | Menu control top-right of the host profile.
Host KYC Break down |  | — | Section heading
Host KYC done at the point of the Signup (IT WILL REDUCE THE TIME OF THE HOST WHEN HE LISTING THE PROPERTY INTO THE PLATFORM ) |  | DONE (13 Aug) | Host KYC moved to signup. (Also found: web hosts had never been KYC'd at all — closed.)
Only left with the Property Listing |  | DONE (13 Aug) | After signup-KYC, hosts go straight to listing.
USER KYC |  | — | Section heading
User can Login and Register without KYC (IT WILL REDUCE TIME TO USER EXPLORE THE APP AND THE PROPERTIES NEAR BY.) |  | DONE (13 Aug) | Renters register and explore without KYC.
At the time before booking user can be do KYC before Booking |  | DONE (13 Aug) | KYC required at booking time only — with the interrupted-booking recovery above.

## Host
Homepage | — | Section heading
Welcome First Name messeage should be appear on top | VERIFIED — already works | 'Hi, {first name}! 👋' renders at the top of the host home.
Improve slider | DONE (earlier) | Host home rebuilt: earnings card, stat grid, trend card, ongoing list.
Show Illustraion on No on going booking | DONE (16 Aug) | Was a 30px grey icon that read as a rendering failure. Now an animated illustration + 'when a guest checks in, their stay shows up here.'
Dicuss Home page | DISCUSSION | Host home rebuilt — bring remaining points to the discussion.
Fix Support Button | DONE (16 Aug) | Support button was wired but its links were dead on Android 11+ (package-visibility). Fixed; WhatsApp/call/email verified launching.

## Common
When app Open Flash app logo with tag line with music | Provided by US | BLOCKED — your assets | Logo done (shipped everywhere). Tagline wording + music/audio file still needed from Aajoo — marked 'Provided by US' in this sheet.
Change the background picture of get starting page |  | DONE (earlier) | Getting-started background is a 3-image auto-playing carousel.
Use the same Font for aajoo name across all the platforms |  | DONE (16 Aug) | The website asked for Fraunces in 90 places and never loaded it — everything rendered in Times New Roman. Now loaded; app already used Fraunces. (One residue: web header wordmark uses Plus Jakarta Sans per design decision BR-2 — conflicts with this ask; your call.)
Same for Login Page |  | DONE (16 Aug) | Same font fix covers the login page.
Forget Password (contactus@aajoohomes.com) |  | PARTIAL — confirm mailbox | System emails already send FROM contactus@aajoohomes.com (live). Confirm the mailbox is monitored, and whether it should replace aajoolive@gmail.com as the support address shown in the app.
In home page Put aajoo logo and name mentioned aajoo only |  | DECISION NEEDED | App renders 'aajoo' + 'homes' as a pair. Dropping to 'aajoo' only is a brand call — say the word.
Change the icon for notification |  | DONE (earlier) | Notification bell replaced the profile icon top-right.
In search bar show current location and remove any week or guest |  | DONE (16 Aug) | Search pill shows the real current place; the frozen 'Any week · 1 guest' subtitle removed.
When we slide the map to another area properties are not Apperaing |  | DONE (16 Aug) | Nothing listened to map movement — panning showed the old area's pins. Now re-searches when the camera settles >1.5 km away. Verified: 98 → 53 results on pan.
Set the re center button on map |  | DONE (16 Aug) | Re-center button added (same fix as User row 12).
In filter when we select number of guest make it same like airbnb |  | OPEN — design scope | Airbnb-style guest stepper = filter redesign; needs design.
In advanced Filter |  | — | Section heading
Make a Common Filter For Price |  | OPEN — design scope | Common price filter — part of the same filter redesign.
Make a chip filter property by monthly, per night |  | DECISION NEEDED — contradicts User row 11 | This asks to ADD monthly/per-night chips; User sheet asks to REMOVE weekly/monthly filters. Both can't be built — pick one.
When be Click on the search bar Shows our service loaction areas, (Take example From Air Bnb |  | PARTIAL | Search sheet already shows suggested destinations with live counts. A full 'service areas' showcase like Airbnb = design scope.
when we click on the near by button its not working |  | DONE (16 Aug) | The 'N homes near you ↗' card had no tap handler at all. Now expands into the property list. Verified on device.
When we enter any other place map will not redirect inton another page (acc to current selection) |  | DONE (16 Aug) | Searching another place now re-centres and re-fetches (destination search + pan-to-search).
Make slider for the on the home page for announcements in diffrent colors 4-5 sliders |  | OPEN — design scope | Web has an announcement slider component; the 4–5 coloured-slides version (and app parity) needs content + design.
Show cat, from admin dashboard add icon also |  | DONE (earlier) | Categories come from the admin-managed API with icons.
add find your stay header after cat, listing ng |  | DONE (earlier) | Home layout reordered accordingly.
Need advise for Browse by cat, section |  | DISCUSSION | Browse-by-category advice: current state is API-driven with legacy types hidden; happy to walk through options.

## Post 25 release
Done ? Yes/no | Page No 1 | Get Started Page |  | Comments |  | Status | What changed
|  | Website Open | Make website like this on web its shows like this | LOGO |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | remove thet floating tags from hero section also remove 12k propertirs and other items from hero section |  | ok |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | add background imagesin the slider that using stock colors roght now |  | image |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Remove logo background |  | please provide logo |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | aajoo Font change |  | mention the font |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | In the make this page as a getting started page for example a entry point for user/host who is visiting the website first time so we can redirect them baed on their role |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | In the Nav Bar show getting started page else nothing show in nav bar |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | When USer scroll down the website shows the Explore stays or become a host in nav bar |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Remove notification button From nav bar getting started |  | ok |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Current location is not correct in the search bar but correct in the map |  | ok checking on it |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | replace the category dropdown selector from saefch bar and add calender for check in and checkout date |  | ratings remove |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | add category list in the BD also show all the category in form to select category |  | ok waiting for list |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Remove this as well from the first page |  | ok |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Location cat map remove these |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Explore Now are Become a host button in center |  | no |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | and high lightes |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | remove rates and properties and revires same as attached pciture in the stated page |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Create diffrentinate from here as per choice explore stays or become a host |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Remove support button From here |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Map shoudl look like Homes page, the same desing in the homes page for map |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Remove find your stay from here |  | ok |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | This content should be change provided by uS |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Remove this as well |  | in property details |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | CHange this content as well |  | content be shared |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | we provided |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Remove FAQ and Footer |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Guest Reviws and Footer |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
| Page No 2 Explore STays / Find Your Stay | User Home page |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Remove this directly show the Current location |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | In th Nav bar Shoe Find you stay, Blog and about us and conact us in menu |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | slider small up and down space is too much |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Directly show this in the home page with the current location |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Pre booking button IS not working and Mix these button these are not show interactive |  | button redirect |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Fix these in center like a featuer high lighed |  | place |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | bElow this show home page and remove homepage button from the nav bar |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | as the attched pictuers |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Show 4 -5 listing in the in the home page and right side map same as it is |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Show support button on the home page only |  | profile section |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Chnage the support UI as per the current theme |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
| Page 3 | About US |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | the gap b/w aajoo and the content is too high |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | change the image from here and about US desgin as well |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Content should be provided by us |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Change the image what makes US Diffrent |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Icon as per current market |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | for all across the app and the about US |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Change the mission and Vision icon use animation here |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
| page 4 | Contact uS |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Fix this form |  | aligmnet and call us remove |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
| Page 5 | Menu |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Remove State Regulation from here | remove |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Home page | prebooking |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Remove Support Button From here |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | No Need of support here |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Sho Sate regulations in Footer | ok |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
| Page 6 | Login page |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Change the image her add color image slider/ or animation Same as per app |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Change the Content of login Provided by aajoo |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Login Form didn't look attactive or morden it looks cheap |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
| Page No 7 | Signup account |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Sign up form looks cheap |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | all from as per current market |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Google sign button is not working |  | firebase connection |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Phone number sign up is missing in the flow |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Ask For Signup User or Host same as Login Form buttons |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Make First step of signed up as per email or mobile number |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Login with google |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | In 2nd section take Personal information |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Diddit KYC verification Miss here |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | and when KYC is Begin did not sho te scanner if user do KYC in phone how do they Scan |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Find lternative way when user go for KYC it wil directlyy re direct to the kYC |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Spell aadhar card change |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | FiX the KYC step above when ID infomtion take |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
| Page No 8 | renter Dashboard |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | remove below from nav bar |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | About us |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Contact |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Becomee a host |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Add |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Show Current Weather as per current loaction current loaction |  |  | ok | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | renter profile update also profile picure not update |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | When it verifred from Diddit Remove the choose file |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Form as per current market |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Current Location is not working |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | auto fill the address as per current loaction |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | User and Host Registation from can be same |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Dicussion needed |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
| Page No 9 | Host Dashboad |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | What are you listing |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Booking Prefence |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Catergory |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | tags |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | all of the above do not show these in list |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | show these with Icons and name |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | all icons all across platform looks premuims |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | For reference |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Give current loaction to th user top of the section |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | it will easy to fill the form |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Current loaction is not working here |  | recheck |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Remove Discription From Here |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Guest Form Must be Mordenn |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | it looks cheap |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | max Price pe night/ in price per nigh / ideal Price |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Monthly Price Same |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Suggest Price in example |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Weekly Price |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Aminities with Icons |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Put this below of property details |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | check in check ou time |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Change the check out check in time |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Remove Cuople Freindly |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Remove this party ana group Booking |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Host Name is mission |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | add below Whatapp Number |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Compre these 2 scrren shots when i upload the document |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | then it show the aadhar card |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Diddit Scaaner redirect it auto maticaly |  | no didt |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | KYC auto matically |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Property is nott submiitted |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | When User select the Pg change it accordingly |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | whole form should be change |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Property edit is not avialable whole dash board |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Host Work Space |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | in nav bar remove tis |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Make these slider small both |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Add Support UI Here |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | ongoing page is missing from Host Side |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Host Poperty List Is missing |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Show State Regulations pages here |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Color of host and USer inerface are same |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | When user find an error show them immediatly not the end of the form |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | These buttons are not working |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Once the KYC is done show Verified |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Check All the field and validations all across playfrom and here |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Add Blog and find your liting b utton in nav Bar |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Host blog is diffrent and User blog is diffrent |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | But Connected for major inforaton s in Blogs Like news |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Bot Pengiun support inbox should not open automatautomatically |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Also Bot Penguin is not the part of admin dashboard |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | PRebooking button is nto working in homepage |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | for luxury, add more desing to show luxury UI |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | FIlter are not working on the map |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Also change the desing of the filter in Homes Page that comin from left side |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Move CTA Why guests love aajooHomes from Home page to About us page |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | remove the place to visit section from home page and add to particular property section |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | redesing the Become a host, FAQ and review section |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | in Property detail page , the booking modal that fit in right side is not in good share in POV of Desgin please design that modal correctly |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Add property Form is not as provided in document also add same form in Admin dashboard to add property |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
| Property Detail Page |  |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | In Property Detail page, in top show one big image and replace the slider with Grid to show property images |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | also show no of guest availability |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | No of beds |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Show rating (in AVG with star) |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Show more details on Property Detail page from Property Form/Db |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Meet you host is not Dynamic also hide the host in with stars |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | show host number post booking |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | In property Detail page, Set Map section after Review section |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Make near by places Dynamic abd redesign this section |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Show property Availibility Calender Before property Gallery |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
| Critical | Also i haveb't seen something for double booking that functionality has been built or in working |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
| Property Booking Page |  |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Please Redesign the booking page |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | IMage slider is not correct, not dynamic |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Remove Footer from Property booking final page |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Add host detail in booking page |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Show Cancelation policy button in booking page also |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
| SIde Bar Menu bar |  |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Rename "Home" with "Prebooking" |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Why List with aajoo and State regulation removed from side bar menu but add in footer |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
| Others |  |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Please redesign the About us page and contact us page |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | in contact us page remove suport call icon and add address |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Need to work on the Modal for Booking in on going page |  | ss nedded |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | In Host dashboard Replace Totalspent box with something else |  | ok |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | In Transaction page add a download icon in the listing to downlaod invoice pdf |  | ok |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Support Bot Icon should be shown in only user dashboard/profile page not everywhere |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Welcome back with name in Dashboard |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | add loader and skeleton loader |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | make calender same in whole webapp |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | no notification generated q |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | I havn't seen Sockets messaging work |  |  |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.
|  | Host daash board is not dynamic, please make htings working on real data so we can test in single flow |  | ok |  | SEPARATE SCOPE | Section-0 redesign — separate contract; tracked in AAJOO_SECTION0_TASKLIST.md, not verified in this pass.

## need to Provide by Aajoo
Title | Description | Status | aajoo comment | Dev comment
About us | Need to provide about us final data | Done |  | About page is CMS-driven and identical on web + app.
Logo | Without Background | Done |  | Official logo shipped across web, app (launcher/splash/in-app), favicons and emails on 15–16 Aug.
CTA | Provide Images for CTA at home Page fist CTA | Pending — awaiting images |  | Send the CTA images and we drop them in.